## Sheet1
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee Role | Status
Sprint 1 | Sprint 1 | US01 | As an AI/ML Intern, I want to import the dataset so that preprocessing can begin. | Must | None | AI/ML Intern | Completed
Sprint 1 | Sprint 1 | US02 | As an AI/ML Intern, I want to preprocess and clean the data so the model receives high-quality inputs. | Must | US01 | AI/ML Intern | Completed
Sprint 1 | Sprint 1 | US03 | As an AI/ML Intern, I want to perform EDA to understand feature impact and distributions. | Should | US02 | AI/ML Intern | Completed
Sprint 2 | Sprint 2 | US04 | As an AI/ML Intern, I want to train ML models (Random Forest, Logistic Regression) to predict loan approval. | Must | US02 | AI/ML Intern | Completed
Sprint 2 | Sprint 2 | US05 | As a Tester, I want to evaluate model performance to ensure accuracy and reliability. | Must | US04 | Tester | Completed
Sprint 2 | Sprint 2 | US06 | As an AI/ML Intern, I want to tune model thresholds so risk bands are meaningful. | Could | US05 | AI/ML Intern | Completed
Sprint 3 | Sprint 3 | US07 | As an AI/ML Intern, I want to integrate SHAP explainability so users understand model results. | Must | US04 | AI/ML Intern | In Progress
Sprint 3 | Sprint 3 | US08 | As a Developer, I want to generate PDF reports so users can download evaluation summaries. | Should | US07 | Developer | In Progress
Sprint 3 | Sprint 3 | US09 | As a Tester, I want to verify report accuracy so the system provides correct insights. | Should | US08 | Tester | Completed
Sprint 4 | Sprint 4 | US10 | As a User, I want a chatbot so I can ask financial questions easily. | Must | None | Developer | Completed
Sprint 4 | Sprint 4 | US11 | As a Developer, I want to deploy the application so users can access it online. | Must | US10 | Developer | In Progress
Sprint 4 | Sprint 4 | US12 | As a Tester, I want to validate system security and input handling. | Should | US11 | Tester | In Progress