## Sheet1
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | AI/ML Intern | 2025-09-23 | Dataset failed to load due to incorrect file path | Sprint 1 | AI/ML Intern | Functional Defect | Corrected the file path and added exception handling | 2025-09-22 | Closed
2 | AI/ML Intern | 2025-09-30 | Preprocessing crashed because of null values in dataset | Sprint 1 | AI/ML Intern | Data Defect | Added null handling + default replacements | 2025-09-29 | Closed
3 | AI/ML Intern | 2025-10-08 | Model training stopped due to datatype mismatch | Sprint 2 | AI/ML Intern | Functional Defect | Implemented datatype validation + conversion | 2025-10-07 | Closed
4 | AI/ML Intern | 2025-10-15 | Trained model (.pkl) was corrupted and failed to load | Sprint 2 | AI/ML Intern | Technical Defect | Re-trained and replaced corrupted model file | 2025-10-15 | Closed
5 | AI/ML Intern | 2025-10-21 | Prediction function failed when model wasn’t loaded | Sprint 3 | AI/ML Intern | Functional Defect | Added model load validation before prediction | 2025-10-21 | Closed
6 | AI/ML Intern | 2025-10-31 | Chatbot returned irrelevant responses for invalid queries | Sprint 4 | AI/ML Intern | Functional Defect | Added fallback response and improved intent recognition | 2025-10-31 | Closed